## Instructions
Cutover Plan Template
Purpose
Run a go-live hour by hour, with owners, dependencies, go or no-go gates and rollback points. Replace the synthetic sample with your own.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Dynamics 365 Group. No vendor workbook, template, branding, or dataset was used. All figures are synthetic.
What’s in this workbook
Runbook |  | One row per cutover step.
Gates |  | Go or no-go decisions.
Dashboard |  | As-of time and headline numbers.
How to use this workbook
1. Enable Editing if Excel opens in Protected View.
2. List your gates on Gates, each with a unique ID and a decision.
3. Replace the sample steps on Runbook. Every step needs a unique Step ID, a start time, hours from 0 to 1,000, a status, Critical path, Rollback point and a Gate ID.
4. During the cutover, update each status and set the as-of time on Dashboard. Times compare to the nearest minute.
5. IDs are compared exactly as typed, so a * or ? in an ID is just a character. A missing start, hours that are missing, negative or above 1,000, or a blank as-of time shows Check times. A missing Step ID or input, or an unknown or duplicate ID, shows Check data. Progress and Critical path status stop until Data check reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: choose File > Import > Upload and pick Insert new sheet(s). Formatting can differ, so check the results, dropdowns and colours after import.
Limitations
Runbook holds up to 299 steps and Gates up to 49 gates.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →

## Runbook
Step ID | Workstream | Activity | Owner | Planned start | Hours | Predecessor | Status | Critical path | Rollback point | Gate ID | Planned finish | Late | Dependency | Gate check | Row check
C-01 | Business | Freeze legacy transactions | Ops lead | 2027-06-18 18:00 | 1 |  | Done | Y | N | G1 | 2027-06-18 19:00 | OK |  | OK | OK
C-02 | Technical | Back up legacy database | IT lead | 2027-06-18 19:00 | 2 | C-01 | Done | Y | Y | G1 | 2027-06-18 21:00 | OK | OK | OK | OK
C-03 | Data | Extract final balances | Data lead | 2027-06-18 21:00 | 3 | C-02 | Done | Y | N | G1 | 2027-06-19 | OK | OK | OK | OK
C-04 | Data | Load masters to production | Data lead | 2027-06-19 | 4 | C-03 | Done | Y | N | G2 | 2027-06-19 04:00 | OK | OK | OK | OK
C-05 | Data | Load open transactions | Data lead | 2027-06-19 04:00 | 5 | C-04 | Done | Y | Y | G2 | 2027-06-19 09:00 | OK | OK | OK | OK
C-06 | Technical | Enable integrations | Integration lead | 2027-06-19 06:00 | 2 | C-05 | Done | N | N | G2 | 2027-06-19 08:00 | OK | Conflict | OK | OK
C-07 | Business | Reconcile trial balance | Controller | 2027-06-19 09:00 | 3 | C-05 | In progress | Y | N | G3 | 2027-06-19 12:00 | Late | OK | OK | OK
C-08 | Business | Reconcile inventory | Warehouse lead | 2027-06-19 09:00 | 4 | C-05 | Blocked | N | N | G3 | 2027-06-19 13:00 | Late | OK | OK | OK
C-09 | Technical | Security roles smoke test | IT lead | 2027-06-19 12:00 | 2 | C-06 | Not started | N | N | G3 | 2027-06-19 14:00 | OK | OK | OK | OK
C-10 | Business | Go or no-go decision | Sponsor | 2027-06-19 16:00 | 1 | C-07 | Not started | Y | Y | G3 | 2027-06-19 17:00 | OK | OK | OK | OK
C-11 | Business | Open system to users | Ops lead | 2027-06-20 06:00 | 1 | C-10 | Not started | Y | N | G4 | 2027-06-20 07:00 | OK | OK | OK | OK
C-12 | Support | Hypercare day 1 check-in | Support lead | 2027-06-20 12:00 | 1 | C-11 | Not started | N | N | G4 | 2027-06-20 13:00 | OK | OK | OK | OK
Formulas:
Planned finish = IF(COUNTA([Step ID]:[Gate ID])=0,"",IF(AND(ISNUMBER([Planned start]),ISNUMBER([Hours]),N([Hours])>=0,N([Hours])<=1000),[Planned start]+[Hours]/24,"n/a"))

## Gates
Gate ID | Gate | Decision time | Gate owner | Decision | Steps done | Row check
G1 | Legacy frozen and backed up | 2027-06-18 23:59 | IT lead | Go | 100% | OK
G2 | Data loaded | 2027-06-19 09:00 | Data lead | Go | 100% | OK
G3 | Business sign-off | 2027-06-19 17:00 | Sponsor | Pending | 0% | OK
G4 | Users live | 2027-06-20 13:00 | Sponsor | Pending | 0% | OK

## Dashboard
Cutover Plan Template
As-of time | 2027-06-19 13:30 | Type the current time at each check-in. Times compare to the nearest minute.
Runbook steps | 12 | Rows with any input, with or without a Step ID.
Steps done | 6 | Status is Done.
Progress by planned hours | 58.62% | Done hours over all hours; stops until Data check reads OK.
Critical-path steps late | 1 | Past planned finish and not done.
Critical path status | Behind | Behind the minute a critical step overruns; stops on bad data.
Blocked steps | 1 | Status is Blocked.
Rollback points left | 1 | Rollback points not yet passed.
Dependency conflicts | 1 | Starts before its predecessor finishes.
Gates pending | 2 | No decision yet.
Rows with time problems | 0 | A missing start, or hours that are missing, negative or above 1,000.
Unknown IDs | 0 | A predecessor or gate that does not exist, or a shared predecessor.
Step IDs to fix | 0 | A row with no Step ID, or a shared one.
Step inputs to check | 0 | A missing status, Y or N, or Gate ID.
Gate rows to fix | 0 | No Gate ID, a shared one, or no decision.
Data check | OK | Do not rely on progress or status until this reads OK.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →