## Instructions
Data Migration Plan Template
Purpose
Track each data object from source to target, with owner, load order, mock results and reconciliation. Reconciled measures record-count coverage only, not amounts or balances. Replace the synthetic sample with your own.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Dynamics 365 Group. No vendor workbook, template, branding, or dataset was used. All figures are synthetic.
What’s in this workbook
Objects |  | One row per data object.
Loads |  | One row per object per mock.
Dashboard |  | Threshold, reported mock and headline numbers.
How to use this workbook
1. Enable Editing if Excel opens in Protected View.
2. List your data objects on Objects, each with a unique ID and a load order. If an object loads separately for two legal entities, give each its own ID, such as DM-02-US and DM-02-CA.
3. Add one row to Loads for each object in each mock.
4. Set the threshold and the mock to report on Dashboard.
5. Set Sign-off to Y only after the business owner accepts the object, including any amount, balance, key and relationship checks that apply. Keep that evidence separately.
6. Fix every Row check, Order check and Object check that is not OK. Readiness reads Check data until Data check reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: choose File > Import > Upload and pick Insert new sheet(s). Formatting can differ, so check the results, dropdowns and colours after import.
Limitations
Objects holds up to 299 rows and Loads up to 999. Reconciled compares record counts only, so matching counts can sit beside wrong amounts or balances, and the threshold is not an acceptable financial discrepancy.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →

## Objects
Object ID | Data object | Source | Target in Dynamics 365 | Owner | Load order | Depends on | Source records | In scope | Cleansing status | Sign-off | Loaded | Reconciled | Readiness | Order check | Excess | Row check
DM-01 | Chart of accounts | Legacy GL | Main accounts | Finance lead | 1 |  | 420 | 380 | Done | Y | 380 | 100% | Ready | OK | OK | OK
DM-02 | Customers | Legacy AR | Customers | Sales ops | 2 |  | 5200 | 4800 | Done | Y | 4796 | 99.92% | Ready | OK | OK | OK
DM-03 | Vendors | Legacy AP | Vendors | AP lead | 2 |  | 1300 | 1150 | Done | N | 1150 | 100% | Not ready | OK | OK | OK
DM-04 | Items | Legacy inventory | Released products | Supply chain | 3 |  | 9000 | 7600 | In progress | N | 7450 | 98.03% | Not ready | OK | OK | OK
DM-05 | Open AR invoices | Legacy AR | Customer open transactions | AR lead | 4 | DM-02 | 2100 | 2100 | Done | Y | 2100 | 100% | Ready | OK | OK | OK
DM-06 | Open AP invoices | Legacy AP | Vendor open transactions | AP lead | 4 | DM-03 | 900 | 900 | Done | Y | 897 | 99.67% | Ready | OK | OK | OK
DM-07 | Open sales orders | Legacy order entry | Sales orders | Sales ops | 3 | DM-04 | 650 | 600 | In progress | N | 590 | 98.33% | Not ready | Order conflict | OK | OK
DM-08 | Inventory on hand | Legacy inventory | On-hand journal | Warehouse lead | 5 | DM-04 | 7600 | 7600 | Not started | N | 7200 | 94.74% | Not ready | OK | OK | OK

## Loads
Object ID | Mock | Records loaded | Records failed | Object check
DM-01 | 1 | 375 | 5 | OK
DM-02 | 1 | 4700 | 100 | OK
DM-03 | 1 | 1100 | 50 | OK
DM-04 | 1 | 7000 | 600 | OK
DM-05 | 1 | 2050 | 50 | OK
DM-06 | 1 | 880 | 20 | OK
DM-07 | 1 | 520 | 80 | OK
DM-08 | 1 | 0 | 0 | OK
DM-01 | 2 | 380 | 0 | OK
DM-02 | 2 | 4796 | 4 | OK
DM-03 | 2 | 1150 | 0 | OK
DM-04 | 2 | 7450 | 150 | OK
DM-05 | 2 | 2100 | 0 | OK
DM-06 | 2 | 897 | 3 | OK
DM-07 | 2 | 590 | 10 | OK
DM-08 | 2 | 7200 | 400 | OK

## Dashboard
Data Migration Plan Template
Reconciliation threshold | 99.5% | My practice, not a Microsoft figure. Compared unrounded, on record counts only.
Mock to report | 2 | Which mock cycle the totals read.
Data objects in plan | 8 | Rows with an Object ID.
Records in scope | 25130 | After cleansing; a duplicate ID counts nowhere until fixed.
Records loaded | 24563 | In the reported mock, for objects in the plan.
Overall reconciliation | 97.74% | Loaded over in scope: record counts only, not amounts.
Objects ready | 4 | Cleansed, signed off, order OK and inside the threshold.
Readiness | 50% | Objects ready over all objects; Check data until Data check reads OK.
Load-order conflicts | 1 | Loads at or before the object it depends on.
Failed records | 567 | In the reported mock.
Objects over-loaded | 0 | More records loaded than in scope.
Order rows to check | 0 | A blank order or an unknown or duplicate dependency.
Load rows to check | 0 | A load with no object, an ambiguous one, or a missing count.
Object rows to check | 0 | No ID, a shared ID, or a missing scope, status or sign-off.
Dashboard inputs missing | 0 | The threshold or the mock to report.
Data check | OK | Do not rely on readiness until this reads OK.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →