## Instructions
ERP Implementation Project Plan Template
Purpose
Plan a Dynamics 365 rollout by phase and task. Replace the synthetic sample with your own.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Dynamics 365 Group. No vendor workbook, template, branding, or dataset was used. All figures are synthetic.
What’s in this workbook
Phases |  | Phase register and rollups.
Tasks |  | One row per task.
Dashboard |  | Status date and headline numbers.
How to use this workbook
1. Enable Editing if Excel opens in Protected View.
2. Set phases and budgets on Phases.
3. Replace the tasks on Tasks.
4. Set the status date on Dashboard.
5. Record the business approval (who and when) before cutover starts on T-11.
6. A row with a missing, reversed or out-of-range date (use 1950 to 2099) shows Check dates, and percent complete shows Check dates until you fix it.
7. Fix every Row check that is not OK. Every task needs a unique Task ID, a listed Phase ID, costs of 0 or more and a percent complete from 0% to 100%. Type 0 for no cost, because a blank is treated as missing.
8. Phase % complete, phase Budget remaining, Overall % complete, Budget remaining, Budget used, Late tasks and Dependency conflicts stop on Check data or Check dates until Data check on Dashboard reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: choose File > Import > Upload and pick Insert new sheet(s). Formatting can differ, so check the results, dropdowns and colours after import.
Limitations
Tasks holds up to 299 rows and Phases up to 49.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →

## Phases
Phase ID | Phase | Budget | Planned cost | Actual cost | % complete | Budget remaining | Row check
PH1 | Mobilize | 20000 | 20000 | 19500 | 100% | 500 | OK
PH2 | Design | 45000 | 45000 | 40000 | 87.37% | 5000 | OK
PH3 | Build | 90000 | 90000 | 24000 | 20.69% | 66000 | OK
PH4 | Data migration | 35000 | 35000 | 12000 | 28.49% | 23000 | OK
PH5 | Testing | 40000 | 40000 | 0 | 0% | 40000 | OK
PH6 | Deploy and hypercare | 30000 | 30000 | 0 | 0% | 30000 | OK

## Tasks
Task ID | Phase ID | Task | Owner | Start | Finish | Predecessor | Planned cost | Actual cost | % complete | Duration days | Earned days | Status | Dependency | Row check
T-01 | PH1 | Project charter and governance | Sponsor | 2027-01-04 | 2027-01-15 |  | 8000 | 8500 | 100% | 12 | 12 | Done |  | OK
T-02 | PH1 | Environment and tenant setup | Partner | 2027-01-11 | 2027-01-22 | T-01 | 12000 | 11000 | 100% | 12 | 12 | Done | Conflict | OK
T-03 | PH2 | Fit-gap workshops | Partner | 2027-01-25 | 2027-02-19 | T-02 | 30000 | 31000 | 100% | 26 | 26 | Done | OK | OK
T-04 | PH2 | Solution design sign-off | Sponsor | 2027-02-22 | 2027-03-05 | T-03 | 15000 | 9000 | 60% | 12 | 7.2 | Late | OK | OK
T-05 | PH3 | Configuration sprints | Partner | 2027-03-01 | 2027-04-23 | T-04 | 60000 | 20000 | 30% | 54 | 16.2 | In progress | Conflict | OK
T-06 | PH3 | Integrations and extensions | Partner | 2027-03-15 | 2027-04-30 | T-04 | 30000 | 4000 | 10% | 47 | 4.7 | In progress | OK | OK
T-07 | PH4 | Data mapping and cleansing | Data lead | 2027-02-15 | 2027-03-12 | T-03 | 15000 | 12000 | 80% | 26 | 20.8 | Late | Conflict | OK
T-08 | PH4 | Mock data loads | Data lead | 2027-03-15 | 2027-04-30 | T-07 | 20000 | 0 | 0% | 47 | 0 | In progress | OK | OK
T-09 | PH5 | System and integration testing | Test lead | 2027-05-03 | 2027-05-21 | T-05 | 15000 | 0 | 0% | 19 | 0 | Not started | OK | OK
T-10 | PH5 | UAT and user training | Business leads | 2027-05-24 | 2027-06-11 | T-09 | 25000 | 0 | 0% | 19 | 0 | Not started | OK | OK
T-11 | PH6 | Readiness review and cutover | Partner | 2027-06-14 | 2027-06-20 | T-10 | 18000 | 0 | 0% | 7 | 0 | Not started | OK | OK
T-12 | PH6 | Hypercare | Support lead | 2027-06-21 | 2027-07-16 | T-11 | 12000 | 0 | 0% | 26 | 0 | Not started | OK | OK

## Dashboard
ERP Implementation Project Plan Template
Status date | 2027-03-15
Overall % complete | 32.21% | Earned days over task days; stops until Data check reads OK.
Total budget | 260000 | Sum of phase budgets.
Actual cost to date | 95500 | Sum of actual cost on rows with a Task ID.
Budget remaining | 164500 | Budget less actual; stops until Data check reads OK.
Budget used | 36.73% | Actual over budget; n/a with no budget.
Late tasks | 2 | Past finish and not done; stops until Data check reads OK.
Dependency conflicts | 3 | Starts before predecessor finishes; stops until Data check reads OK.
Design phase % complete | 87.37% | Phases row 3.
Task days | 307 | Sum of duration days.
Earned days | 98.9 | Sum of earned days.
Date problems | 0 | Tasks with a missing, reversed or out-of-range date.
Task rows to check | 0 | A row with no Task ID, a shared ID, or a missing or out-of-range cost or percent.
Tasks with no phase | 0 | Tasks no phase rollup can see: a blank or unlisted Phase ID.
Phase rows to check | 0 | A phase with no ID, a shared ID, or a missing or out-of-range budget.
Predecessors to check | 0 | A predecessor that matches no Task ID, or more than one.
Status date missing | 0 | The status date is blank, is not a date, or falls outside 1950 to 2099.
Data check | OK | Do not rely on progress, budget or status until this reads OK.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →