## Instructions
Fit-Gap Analysis Template
Purpose
Score each requirement as Standard, Configure, Extend or Gap against Dynamics 365. The sample describes a fictional project and is not a Dynamics 365 capability matrix.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Dynamics 365 Group. No vendor workbook, template, branding, or dataset was used. All figures are synthetic.
What’s in this workbook
Lists |  | What each fit category and priority means.
Requirements |  | One row per requirement.
Summary |  | Counts, fit-to-standard percent, effort and cost by process area.
Dashboard |  | Blended day rate and headline numbers.
How to use this workbook
1. Enable Editing if Excel opens in Protected View.
2. List your process areas on Summary, each name once.
3. Replace the sample requirements on Requirements. Every row needs a unique Req ID, a listed area, a priority, a fit and effort days. Type 0 for no effort, because a blank is treated as missing.
4. Set your own blended day rate on Dashboard. The sample rate is not a quote.
5. Fix every Row check that is not OK. Do not quote a number or approve an extension until Data check on Dashboard reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: choose File > Import > Upload and pick Insert new sheet(s). Formatting can differ, so check the results, dropdowns and colours after import.
Limitations
Requirements holds up to 499 rows and Summary up to 20 process areas. Effort days run from 0 to 100,000 and the day rate from 0 to 1,000,000; a pasted value outside that range shows Check inputs. Area names and Req IDs are matched exactly, so * and ? are ordinary characters. The sample is fictional and says nothing about what Dynamics 365 can do. Effort days are implementation estimates, not a maintenance figure.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →

## Lists
Fit category | Meaning
Standard | Works out of the box with no setup beyond normal parameters.
Configure | Met through settings and workflows, with no code.
Extend | Needs an extension, an ISV solution or a Power Platform build.
Gap | No acceptable answer yet. Change the process or fund a build.
Priority | Meaning
Must | The project cannot go live without it.
Should | Important, and a workaround could hold for a while.
Could | Useful if time and budget allow.

## Requirements
Req ID | Process area | Requirement | Priority | Fit | Effort days | Notes | Estimated cost | Row check
R-01 | Finance | Multi-entity general ledger with intercompany | Must | Standard | 2 |  | 2400 | OK
R-02 | Finance | Fixed asset depreciation books | Should | Configure | 3 |  | 3600 | OK
R-03 | Finance | Custom board reporting pack | Should | Extend | 8 |  | 9600 | OK
R-04 | Procurement | Three-way invoice matching | Must | Standard | 1 |  | 1200 | OK
R-05 | Procurement | Purchase approval by spend limit | Must | Configure | 4 |  | 4800 | OK
R-06 | Procurement | Feed quote returns into the group's in-house tender archive | Could | Gap | 15 |  | 18000 | OK
R-07 | Sales | Customer credit limit holds | Must | Configure | 2 |  | 2400 | OK
R-08 | Sales | Rebate accruals by customer group | Should | Extend | 10 |  | 12000 | OK
R-09 | Sales | Legacy pricing engine replication | Must | Gap | 25 |  | 30000 | OK
R-10 | Warehouse | Barcode receiving | Must | Standard | 3 |  | 3600 | OK
R-11 | Warehouse | Wave picking | Should | Configure | 5 |  | 6000 | OK
R-12 | Warehouse | Custom carrier label integration | Must | Extend | 12 |  | 14400 | OK

## Summary
Process area | Requirements | Standard | Configure | Extend | Gap | Fit to standard | Area days | Area cost | Name check
Finance | 3 | 1 | 1 | 1 | 0 | 66.67% | 13 | 15600 | OK
Procurement | 3 | 1 | 1 | 0 | 1 | 66.67% | 20 | 24000 | OK
Sales | 3 | 0 | 1 | 1 | 1 | 33.33% | 37 | 44400 | OK
Warehouse | 3 | 1 | 1 | 1 | 0 | 66.67% | 20 | 24000 | OK

## Dashboard
Fit-Gap Analysis Template
Blended day rate (sample) | 1200 | Replace with your partner's rate.
Requirements logged | 12 | Rows with a Req ID. Every count on this sheet uses the same rows.
Fit to standard | 58.33% | Standard plus Configure over all requirements.
Gaps | 2 | Requirements scored Gap.
Must-have gaps | 1 | Gaps with priority Must; Check inputs if a gap has no priority.
Extend + Gap effort days | 70 | Estimated implementation effort, not a maintenance figure.
Estimated cost | 108000 | All effort at the blended day rate; Check inputs if any is missing.
Warehouse fit to standard | 66.67% | Summary row 5, under the name you gave it.
Not yet scored | 0 | Requirements with no fit category.
Area not on Summary | 0 | Requirements the area rollup cannot see.
Rows with no Req ID | 0 | Left out of every total until they have an ID.
Duplicate Req IDs | 0 | Rows sharing an ID.
Inputs to check | 0 | A missing or invalid priority, effort or day rate. A typed 0 is not missing.
Duplicate area names | 0 | Later rows with an area name already listed.
Data check | OK | Do not quote a number or approve an extension until this reads OK.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →