## Instructions
UAT Test Plan Template
Purpose
Track test scenarios by process, with testers, results, retests, defects and sign-off. Replace the synthetic sample with your own.
Clean-room disclosure
Clean-room disclosure: every formula, layout, instruction, and sample figure in this workbook was authored from scratch for Dynamics 365 Group. No vendor workbook, template, branding, or dataset was used. All figures are synthetic.
What’s in this workbook
Scenarios |  | One row per test.
Defects |  | One row per defect.
Processes |  | Rollup by process.
Dashboard |  | Report date, threshold and headline numbers.
How to use this workbook
1. Enable Editing if Excel opens in Protected View.
2. List your processes on Processes, each name once.
3. Replace the sample tests on Scenarios. Every row needs a unique Scenario ID, a listed process, a planned date with no time and a priority.
4. Log results as they come in, and log each defect on Defects with a severity and a status.
5. Set the report date and the pass-rate threshold on Dashboard. The pass rate compares unrounded.
6. Fix every Row check and Scenario check that is not OK. Ready for sign-off reads No until Data check reads OK.
Colour legend
Colour legend
Input — enter or edit your own data here
Calculated — formula-driven, please do not overwrite
Output — key result for reporting and dashboards
Using this workbook in Google Sheets
To use this workbook in Google Sheets: choose File > Import > Upload and pick Insert new sheet(s). Formatting can differ, so check the results, dropdowns and colours after import.
Limitations
Scenarios holds up to 499 rows, Defects up to 499 and Processes up to 20.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →

## Scenarios
Scenario ID | Process | Scenario | Tester | Planned date | Priority | Run 1 result | Retest result | Sign-off | Latest result | Open defects | Row check
UAT-01 | Sales | Create and confirm a sales order | Sales ops | 2027-05-24 | Critical | Pass |  | Y | Pass | 0 | OK
UAT-02 | Sales | Credit limit hold and release | Credit controller | 2027-05-24 | High | Fail | Pass | Y | Pass | 0 | OK
UAT-03 | Sales | Return order with credit note | Sales ops | 2027-05-25 | Medium | Fail |  | N | Fail | 1 | OK
UAT-04 | Purchasing | Purchase requisition approval | Buyer | 2027-05-25 | High | Pass |  | Y | Pass | 0 | OK
UAT-05 | Purchasing | Three-way match and invoice post | AP clerk | 2027-05-26 | Critical | Pass |  | Y | Pass | 0 | OK
UAT-06 | Purchasing | Vendor prepayment | AP clerk | 2027-05-26 | Medium | Blocked |  | N | Blocked | 1 | OK
UAT-07 | Finance | Month-end close checklist | Controller | 2027-05-27 | Critical | Pass |  | Y | Pass | 0 | OK
UAT-08 | Finance | Bank reconciliation | Accountant | 2027-05-27 | High | Fail | Fail | N | Fail | 2 | OK
UAT-09 | Finance | Fixed asset acquisition | Accountant | 2027-05-28 | Medium |  |  | N | Not run | 0 | OK
UAT-10 | Inventory | Receive purchase order to warehouse | Warehouse lead | 2027-05-28 | Critical | Pass |  | Y | Pass | 0 | OK
UAT-11 | Inventory | Cycle count and adjustment | Warehouse lead | 2027-06-01 | High |  |  | N | Not run | 0 | OK
UAT-12 | Inventory | Transfer order between sites | Warehouse lead | 2027-06-02 | Medium |  |  | N | Not run | 0 | OK

## Defects
Defect ID | Scenario ID | Severity | Summary | Status | Scenario check
D-01 | UAT-02 | 2 | Hold not released after payment | Closed | OK
D-02 | UAT-03 | 3 | Credit note missing return reason | Open | OK
D-03 | UAT-08 | 1 | Bank statement import fails on CSV | Open | OK
D-04 | UAT-06 | 2 | Prepayment posting profile missing | Fixed | OK
D-05 | UAT-08 | 3 | Matching rule tolerance too strict | Open | OK

## Processes
Business process | Scenarios | Executed | Passed | Pass rate | Blocked | Open defects | Name check
Sales | 3 | 3 | 2 | 66.67% | 0 | 1 | OK
Purchasing | 3 | 3 | 2 | 66.67% | 1 | 1 | OK
Finance | 3 | 2 | 1 | 50% | 0 | 2 | OK
Inventory | 3 | 1 | 1 | 100% | 0 | 0 | OK

## Dashboard
UAT Test Plan Template
Report date | 2027-05-28 | Type the date of each report, with no time.
Sign-off pass-rate threshold | 95% | My practice, not a Microsoft figure. Compared unrounded.
Test scenarios | 12 | Rows with a Scenario ID. Every count uses the same rows.
Executed | 9 | Latest result is not Not run.
Passed | 6 | Latest result is Pass. A retest overrides run 1.
Pass rate | 66.67% | Passed over executed, compared with the threshold unrounded.
Blocked | 1 | Latest result is Blocked.
Open severity-1 defects | 1 | Status is not Closed.
Due but not run | 1 | Planned by the report date, with no result.
Ready for sign-off | No | Yes only when every check passes and Data check reads OK.
Sales pass rate | 66.67% | Processes row 2, under the name you gave it.
Scenarios to date-check | 0 | A planned date that is missing or holds a time.
Process not listed | 0 | Scenarios the process rollup cannot see.
Defect rows to fix | 0 | No ID, no single scenario, or a missing severity or status.
Scenario IDs to fix | 0 | A row with no Scenario ID, or a shared one.
Duplicate process names | 0 | Later rows with a process already listed.
Inputs to check | 0 | A missing priority, threshold or report date.
Data check | OK | Sign-off reads No until this reads OK.
Free template from Dynamics 365 Group: more free Dynamics 365 tools and templates →